## Sheet1
No | Activity ID | Activity Name | Summary Program | Dicipline | Remaining Duration | Start | Finish | Total Float
1 | Arden Station |  |  |  | 1437 | 2018-04-18 | 2022-03-24 | 357
2 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
3 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Arden | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
4 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Arden | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
5 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
6 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Arden | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
7 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Arden | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
8 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
9 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Arden | PS | 47 | 2019-11-08 | 2020-01-30 | 135
10 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Arden | PS | 15 | 2020-04-18 | 2020-05-08 | 305
11 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
12 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Arden | SS | 24 | 2020-07-11 | 2020-08-11 | 260
13 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Arden | SS | 48 | 2021-02-20 | 2021-05-01 | 345
14 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
15 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Arden | MEP | 0 | 2020-09-18 |  | 284
16 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Arden | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
17 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2022-03-24 | 261
18 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Arden | AF | 0 | 2020-08-12 |  | 284
19 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Arden | AF | 36 | 2022-02-08 | 2022-03-24 | 261
20 | Perungalathur Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
21 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
22 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Arden | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
23 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Arden | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
24 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
25 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Arden | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
26 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Arden | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
27 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
28 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Arden | PS | 47 | 2019-11-08 | 2020-01-30 | 135
29 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Arden | PS | 15 | 2020-04-18 | 2020-05-08 | 305
30 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
31 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Arden | SS | 24 | 2020-07-11 | 2020-08-11 | 260
32 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Arden | SS | 48 | 2021-02-20 | 2021-05-01 | 345
33 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
34 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Arden | MEP | 0 | 2020-09-18 |  | 284
35 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Arden | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
36 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
37 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Arden | AF | 0 | 2020-08-12 |  | 284
38 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Arden | AF | 36 | 2022-02-08 | 2024-03-24 | 261