## Sheet1
No | Activity ID | Activity Name | Summary Program | Dicipline | Remaining Duration | Start | Finish | Total Float
1 | Arden Station |  |  |  | 1437 | 2018-04-18 | 2022-03-24 | 357
2 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
3 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Arden | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
4 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Arden | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
5 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
6 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Arden | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
7 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Arden | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
8 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
9 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Arden | PS | 47 | 2019-11-08 | 2020-01-30 | 135
10 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Arden | PS | 15 | 2020-04-18 | 2020-05-08 | 305
11 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
12 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Arden | SS | 24 | 2020-07-11 | 2020-08-11 | 260
13 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Arden | SS | 48 | 2021-02-20 | 2021-05-01 | 345
14 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
15 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Arden | MEP | 0 | 2020-09-18 |  | 284
16 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Arden | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
17 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2022-03-24 | 261
18 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Arden | AF | 0 | 2020-08-12 |  | 284
19 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Arden | AF | 36 | 2022-02-08 | 2022-03-24 | 261
20 | Perungalathur Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
21 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
22 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Perungalathur | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
23 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Perungalathur | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
24 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
25 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Perungalathur | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
26 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Perungalathur | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
27 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
28 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Perungalathur | PS | 47 | 2019-11-08 | 2020-01-30 | 135
29 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Perungalathur | PS | 15 | 2020-04-18 | 2020-05-08 | 305
30 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
31 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Perungalathur | SS | 24 | 2020-07-11 | 2020-08-11 | 260
32 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Perungalathur | SS | 48 | 2021-02-20 | 2021-05-01 | 345
33 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
34 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Perungalathur | MEP | 0 | 2020-09-18 |  | 284
35 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Perungalathur | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
36 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
37 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Perungalathur | AF | 0 | 2020-08-12 |  | 284
38 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Perungalathur | AF | 36 | 2022-02-08 | 2024-03-24 | 261
39 | Tambaram Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
40 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
41 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Tambaram | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
42 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Tambaram | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
43 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
44 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Tambaram | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
45 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Tambaram | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
46 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
47 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Tambaram | PS | 47 | 2019-11-08 | 2020-01-30 | 135
48 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Tambaram | PS | 15 | 2020-04-18 | 2020-05-08 | 305
49 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
50 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Tambaram | SS | 24 | 2020-07-11 | 2020-08-11 | 260
51 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Tambaram | SS | 48 | 2021-02-20 | 2021-05-01 | 345
52 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
53 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Tambaram | MEP | 0 | 2020-09-18 |  | 284
54 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Tambaram | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
55 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
56 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Tambaram | AF | 0 | 2020-08-12 |  | 284
57 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Tambaram | AF | 36 | 2022-02-08 | 2024-03-24 | 261
58 | Crompet Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
59 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
60 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Crompet | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
61 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Crompet | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
62 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
63 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Crompet | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
64 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Crompet | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
65 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
66 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Crompet | PS | 47 | 2019-11-08 | 2020-01-30 | 135
67 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Crompet | PS | 15 | 2020-04-18 | 2020-05-08 | 305
68 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
69 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Crompet | SS | 24 | 2020-07-11 | 2020-08-11 | 260
70 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Crompet | SS | 48 | 2021-02-20 | 2021-05-01 | 345
71 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
72 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Crompet | MEP | 0 | 2020-09-18 |  | 284
73 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Crompet | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
74 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
75 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Crompet | AF | 0 | 2020-08-12 |  | 284
76 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Crompet | AF | 36 | 2022-02-08 | 2024-03-24 | 261
77 | Pallavaram Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
78 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
79 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Pallavaram | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
80 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Pallavaram | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
81 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
82 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Pallavaram | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
83 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Pallavaram | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
84 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
85 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Pallavaram | PS | 47 | 2019-11-08 | 2020-01-30 | 135
86 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Pallavaram | PS | 15 | 2020-04-18 | 2020-05-08 | 305
87 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
88 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Pallavaram | SS | 24 | 2020-07-11 | 2020-08-11 | 260
89 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Pallavaram | SS | 48 | 2021-02-20 | 2021-05-01 | 345
90 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
91 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Pallavaram | MEP | 0 | 2020-09-18 |  | 284
92 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Pallavaram | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
93 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
94 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Pallavaram | AF | 0 | 2020-08-12 |  | 284
95 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Pallavaram | AF | 36 | 2022-02-08 | 2024-03-24 | 261
96 | Tirusulam Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
97 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
98 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Tirusulam | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
99 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Tirusulam | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
100 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
101 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Tirusulam | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
102 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Tirusulam | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
103 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
104 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Tirusulam | PS | 47 | 2019-11-08 | 2020-01-30 | 135
105 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Tirusulam | PS | 15 | 2020-04-18 | 2020-05-08 | 305
106 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
107 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Tirusulam | SS | 24 | 2020-07-11 | 2020-08-11 | 260
108 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Tirusulam | SS | 48 | 2021-02-20 | 2021-05-01 | 345
109 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
110 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Tirusulam | MEP | 0 | 2020-09-18 |  | 284
111 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Tirusulam | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
112 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
113 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Tirusulam | AF | 0 | 2020-08-12 |  | 284
114 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Tirusulam | AF | 36 | 2022-02-08 | 2024-03-24 | 261
115 | Meenambakkam Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
116 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
117 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Meenambakkam | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
118 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Meenambakkam | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
119 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
120 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Meenambakkam | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
121 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Meenambakkam | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
122 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
123 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Meenambakkam | PS | 47 | 2019-11-08 | 2020-01-30 | 135
124 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Meenambakkam | PS | 15 | 2020-04-18 | 2020-05-08 | 305
125 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
126 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Meenambakkam | SS | 24 | 2020-07-11 | 2020-08-11 | 260
127 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Meenambakkam | SS | 48 | 2021-02-20 | 2021-05-01 | 345
128 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
129 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Meenambakkam | MEP | 0 | 2020-09-18 |  | 284
130 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Meenambakkam | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
131 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
132 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Meenambakkam | AF | 0 | 2020-08-12 |  | 284
133 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Meenambakkam | AF | 36 | 2022-02-08 | 2024-03-24 | 261
134 | Pazhavanthangal Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
135 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
136 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Pazhavanthangal | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
137 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Pazhavanthangal | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
138 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
139 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Pazhavanthangal | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
140 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Pazhavanthangal | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
141 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
142 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Pazhavanthangal | PS | 47 | 2019-11-08 | 2020-01-30 | 135
143 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Pazhavanthangal | PS | 15 | 2020-04-18 | 2020-05-08 | 305
144 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
145 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Pazhavanthangal | SS | 24 | 2020-07-11 | 2020-08-11 | 260
146 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Pazhavanthangal | SS | 48 | 2021-02-20 | 2021-05-01 | 345
147 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
148 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Pazhavanthangal | MEP | 0 | 2020-09-18 |  | 284
149 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Pazhavanthangal | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
150 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
151 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Pazhavanthangal | AF | 0 | 2020-08-12 |  | 284
152 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Pazhavanthangal | AF | 36 | 2022-02-08 | 2024-03-24 | 261
153 | St Thomas Mount Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
154 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
155 | ARD.ST.10050 | Arden - West - Construct Guide Wall | St Thomas Mount | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
156 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | St Thomas Mount | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
157 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
158 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | St Thomas Mount | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
159 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | St Thomas Mount | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
160 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
161 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | St Thomas Mount | PS | 47 | 2019-11-08 | 2020-01-30 | 135
162 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | St Thomas Mount | PS | 15 | 2020-04-18 | 2020-05-08 | 305
163 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
164 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | St Thomas Mount | SS | 24 | 2020-07-11 | 2020-08-11 | 260
165 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | St Thomas Mount | SS | 48 | 2021-02-20 | 2021-05-01 | 345
166 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
167 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | St Thomas Mount | MEP | 0 | 2020-09-18 |  | 284
168 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | St Thomas Mount | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
169 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
170 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | St Thomas Mount | AF | 0 | 2020-08-12 |  | 284
171 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | St Thomas Mount | AF | 36 | 2022-02-08 | 2024-03-24 | 261
172 | Guindy Station |  |  |  | 1437 | 2018-04-18 | 2024-03-24 | 357
173 | Piling Works |  |  |  | 179 | 2018-04-18 | 2018-12-20 | 127
174 | ARD.ST.10050 | Arden - West - Construct Guide Wall | Guindy | Piling | 26 | 2018-04-18 | 2018-05-23 | 86
175 | ARD.ST.20100 | Arden - East - Piling (Diaphragm Wall) | Guindy | Piling | 96 | 2018-08-10 | 2018-12-20 | 127
176 | Excavation Works |  |  |  | 203 | 2018-08-10 | 2019-06-14 | 127
177 | ARD.ST.10200 | Arden - West - Excavate and Strut to Invert Level (Level B3) | Guindy | Excav | 83 | 2018-08-10 | 2018-12-01 | 86
178 | ARD.ST.20200 | Arden - East - Excavate and Strut to Invert Level (Level B3) | Guindy | Excav | 113 | 2018-12-13 | 2019-06-14 | 127
179 | Primary Structure |  |  |  | 115 | 2019-11-08 | 2020-05-08 | 305
180 | ARD.ST.21100 | Arden - East - Construct Concourse Level Slab (Level B1) | Guindy | PS | 47 | 2019-11-08 | 2020-01-30 | 135
181 | ARD.ST.13300 | Arden - West - Complete Stripping Formwork and Remove Temporary Props Supporting Level B1 | Guindy | PS | 15 | 2020-04-18 | 2020-05-08 | 305
182 | Secondary Structure |  |  |  | 195 | 2020-07-11 | 2021-05-01 | 345
183 | ARD.ST.13400 | Arden - West - Construct Platform Centre Section (Level B2 - Platform Level) | Guindy | SS | 24 | 2020-07-11 | 2020-08-11 | 260
184 | ARD.ST.22500 | Arden - East - Construct Platform Outside Section (Level B2 - Platform Level) | Guindy | SS | 48 | 2021-02-20 | 2021-05-01 | 345
185 | MEP Fit Off |  |  |  | 347 | 2020-09-18 | 2022-01-14 | 228
186 | ARD.PM.10470 | Arden - West - Platform Level Building Services Rooms Ready for Building Servcies | Guindy | MEP | 0 | 2020-09-18 |  | 284
187 | ARD.FO.82920 | Arden - East - Install Platform Screen Doors System | Guindy | MEP | 47 | 2021-10-29 | 2022-01-14 | 228
188 | Architectural Finishes |  |  |  | 429 | 2020-08-12 | 2024-03-24 | 261
189 | ARD.PM.10450 | Arden - West - Platform 'Back of House' Ready for Fitout - B2 | Guindy | AF | 0 | 2020-08-12 |  | 284
190 | ARD.FO.12700 | Arden - East - Install Station Furniture, Signage and Lighting - B1 | Guindy | AF | 36 | 2022-02-08 | 2024-03-24 | 261